## Sheet1
Name | 2/28/2024 | 3/1/2024 | 3/4/2024 | 3/6/2024 | 3/8/2024
Joseph Kirby | Figure out how to find the camera angle from center when detecting an aruco marker | Establish FOV of the camera to find angle of aruco marker within around a degree as a backup plan to calibration | Work towards figuring out the calibration of the camera to obtain the camera matrix with rotation and translation vectors the then get the angle from the aruco marker | Pivoted towards making the backup plan(FOV angle) more accurate through a series of tests using the aruco marker at various angles to see the accuracy of our FOV calculated angle and the angle away the marker is from the camera. | Implemented LCD display for demo 1, help Jonah with angle detection
Hunter Burnham | Figure out how to find the camera angle via calibration and to get the camera matrix | Continue work on calibration and figuring out the camera matrix code from OpenCV | Work towards figuring out the calibration of the camera to obtain the camera matrix with rotation and translation vectors the then get the angle from the aruco marker | Continued work on the calibration technique of figuring out the camera matrix, was working through troubleshooting the variance of the results. | Worked on calibration accuracy and refining pose estimation prior to the demo.
Jonah Bertolino | Figure out the distance away the aruco marker is from the camera | Establish horizontal FOV which correlates to angle away from center in the x direction | Work towards figuring out the calibration of the camera to obtain the camera matrix with rotation and translation vectors the then get the angle from the aruco marker | Pivoted towards making the backup plan(FOV angle) more accurate through a series of tests using the aruco marker at various angles to see the accuracy of our FOV calculated angle and the angle away the marker is from the camera. | Continued refining the the FOV camera angle detection to get within around 0.3 degrees accuracy.
Joel Shorey | Finish up the MiniProject documentation and get up to speed on driving the robot straight
Caden Nubel